## Team Information
Team Member Information
No. | Name | Student ID | Email
1 | Le Xuan Ny | 105680151 | 105680151@student.swin.edu.au
2 | Pahan Pathirathna | 104657523 | 104657523@student.swin.edu.au
3 | Nguyen Quang Khai | 105560512 | 105560512@student.swin.edu.au
4 | Pham Dinh Duc Anh | 105202964 | 105202964@student.swin.edu.au
5 | Pham Nguyen Minh Hoang | 105543500 | 105543500@student.swin.edu.au
6 | Truong Ngoc Gia Hieu | 105565520 | 105565520@student.swin.edu.au

## Weekly Tasks
Weekly Tasks
No. | Task | Description | Start Date | End Date | Responsible | Resource | Link | Status | Note | Sample Template
Week 04 (Oct 5th - 11th, 2026)
1 | Write Group Styles and Roles | - Who does what and how will you work together? - Who will be responsible for submitted deliverables? - Who will ask questions on behalf of their group? | 2026-10-09 | 2026-10-17 | Ny | Project Description | Google Docs | Completed
2 | Write RECOMMENDATION Timeline | - What are the key milestones from Week 5 to Week 11 to ensure project completion? - How will tasks be broken down across weeks (e.g., using WBS or Gantt chart milestones)? - Who is responsible for allocating 2-3 final days (end of Week 11) exclusively for rigorous testing and debugging? - Detailed roadmap & WBS available in 'Project Timeline' sheet (Weeks 5-11 + testing phase). | 2026-10-09 | 2026-10-17 | Pahan |  |  | Completed | Need more detail | Project Sample Timeline
3 | Write RECOMMENDATION Communication Plan | - What communication channels and tools will the group use (e.g., Slack, Zoom, Google Drive)? - How frequently will regular team check-ins or meetings take place? - What are the expectations and response timeframes for team member replies? | 2026-10-09 | 2026-10-17 | Khai |  |  | Completed | Fill in the Sample Template
4 | Write On-track behaviors | - What specific actions and habits demonstrate active participation and reliability within the group? - How will team members proactively update others on task progress and roadblocks? - What standards of mutual support and accountability ensure the project stays on schedule? | 2026-10-09 | 2026-10-17 | Duc Anh |  |  | Completed | Fix the format
5 | Write Off-track behaviors | - What specific actions or communication gaps indicate a team member is falling behind or disconnecting? - How will the group address missed deadlines, unresponsiveness, or lack of contribution constructively? - What corrective measures or escalation steps are in place if a member goes off-track? | 2026-10-09 | 2026-10-17 | Hoang |  |  | Completed | Hoang sent privately to Hieu
6 | Write Resolving Tensions | - How will the group approach and manage interpersonal conflicts or disagreements constructively? - What process is established for open dialogue, compromise, and collective decision-making? - At what point and how should conflicts be escalated (e.g., involving instructors or peers) if internal resolution fails? | 2026-10-09 | 2026-10-17 |  |  |  | Completed
7 | Write Team Expectations | - What are the shared standards regarding code quality, documentation, and timely delivery? - How do members expect to support one another in achieving high academic and project performance? - What mutual commitments ensure everyone contributes fairly and meets the group's goals? | 2026-10-09 | 2026-10-17 | Hieu |  |  | Completed

## Project Timeline
Project Timeline
| Project Title |  | Start Date
| Facial Recognition with Emotion & Liveness |  | 2026-10-08
| Project Manager |  | End Date
| Mr. Truong Ngoc Gia Hieu |  | 2026-11-25
WBS NO. | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS
Task 1 | Task 1 - PROJECT INITIATION AND PLANNING | In Progress | All Members | 2026-10-08 | 2026-10-13 | 6
2026-01-01 | Review assignment brief, datasets, marking scheme and model restrictions | Complete | Team | 2026-10-08 | 2026-10-09 | 2
2026-02-01 | Confirm project scope, member responsibilities and technical workstream leads | Complete | Team | 2026-10-08 | 2026-10-10 | 3
2026-03-01 | Approve milestone dates, task dependencies and project timeline | Complete | Team | 2026-10-09 | 2026-10-11 | 3
2026-04-01 | Choose frameworks, shared repository and communication workflow | Not Started | Team | 2026-10-09 | 2026-10-12 | 4
2026-05-01 | Set up Python environment, libraries and folder structure | Not Started | Team | 2026-10-10 | 2026-10-13 | 4
2026-06-01 | Select candidate datasets and agree data/privacy safeguards | Not Started | Team | 2026-10-11 | 2026-10-13 | 3
Task 2 | Task 2 - DATA PREPARATION & MODEL BASELINES | Not Started | All Members | 2026-10-12 | 2026-10-20 | 9
2026-01-02 | Organize identity classification training, validation and test datasets | Not Started | Team | 2026-10-12 | 2026-10-15 | 4
2026-02-02 | Check verification_pairs_val.txt paths, identities and binary labels | Not Started | Team | 2026-10-12 | 2026-10-15 | 4
2026-03-02 | Implement face cropping, resizing, normalization and augmentation | Not Started | Team | 2026-10-14 | 2026-10-18 | 5
2026-04-02 | Prepare real-face and spoof-face datasets with disjoint splits | Not Started | Team | 2026-10-14 | 2026-10-18 | 5
2026-05-02 | Prepare emotion dataset, train/validation splits and class definitions | Not Started | Team | 2026-10-14 | 2026-10-19 | 6
2026-06-02 | Agree module input/output contracts and saved-model interfaces | Not Started | Team | 2026-10-16 | 2026-10-19 | 4
2026-07-02 | Run baseline loading, shape and one-batch training smoke tests | Not Started | Team | 2026-10-19 | 2026-10-20 | 2
Task 3 | Task 3 - FACE VERIFICATION: BOTH REQUIRED METHODS | Not Started | All Members | 2026-10-16 | 2026-11-08 | 24
2026-01-03 | Train a classification-based CNN on known identity labels | Not Started | Team | 2026-10-16 | 2026-10-24 | 9
2026-02-03 | Extract fixed-length embeddings from the classification model | Not Started | Team | 2026-10-22 | 2026-10-26 | 5
2026-03-03 | Implement pair/triplet sampling and metric-learning loss | Not Started | Team | 2026-10-19 | 2026-10-25 | 7
2026-04-03 | Train and tune the metric-learning embedding CNN | Not Started | Team | 2026-10-25 | 2026-11-02 | 9
2026-05-03 | Calculate cosine similarity and Euclidean distance scores | Not Started | Team | 2026-10-30 | 2026-11-04 | 6
2026-06-03 | Evaluate both models using verification_pairs_val.txt, ROC and AUC | Not Started | Team | 2026-11-03 | 2026-11-07 | 5
2026-07-03 | Choose verification threshold and unknown-person rejection rule | Not Started | Team | 2026-11-06 | 2026-11-08 | 3
Task 4 | Task 4 - ANTI-SPOOFING / LIVENESS MODEL | Not Started | All Members | 2026-10-18 | 2026-11-06 | 20
2026-01-04 | Choose and implement a trainable anti-spoofing CNN | Not Started | Team | 2026-10-18 | 2026-10-21 | 4
2026-02-04 | Train anti-spoofing model on live and spoof face images | Not Started | Team | 2026-10-22 | 2026-11-01 | 11
2026-03-04 | Evaluate spoof rejection, errors and decision threshold | Not Started | Team | 2026-10-31 | 2026-11-04 | 5
2026-04-04 | Package real-time liveness prediction for system integration | Not Started | Team | 2026-11-03 | 2026-11-06 | 4
Task 5 | Task 5 - EMOTION DETECTION MODEL | Not Started | All Members | 2026-10-18 | 2026-11-06 | 20
2026-01-05 | Choose emotion labels and design the trainable CNN | Not Started | Team | 2026-10-18 | 2026-11-21 | 35
2026-02-05 | Train and validate the emotion classification CNN | Not Started | Team | 2026-10-22 | 2026-11-01 | 11
2026-03-05 | Evaluate accuracy, per-class results and common errors | Not Started | Team | 2026-10-31 | 2026-11-04 | 5
2026-04-05 | Package real-time emotion labels and optional icon mapping | Not Started | Team | 2026-11-03 | 2026-11-06 | 4
Task 6 | Task 6 - REAL-TIME UI & SYSTEM INTEGRATION | Not Started | All Members | 2026-10-20 | 2026-11-18 | 30
2026-01-06 | Design the webcam UI mock-up, screen flow and status display | Not Started | Team | 2026-10-20 | 2026-10-25 | 6
2026-02-06 | Implement webcam capture and face detection/cropping | Not Started | Team | 2026-10-24 | 2026-10-30 | 7
2026-03-06 | Add employee registration and saved reference embeddings | Not Started | Team | 2026-10-29 | 2026-11-05 | 8
2026-04-06 | Integrate face embeddings, similarity threshold and identity labels | Not Started | Team | 2026-11-07 | 2026-11-11 | 5
2026-05-06 | Integrate liveness gate to block spoof attendance | Not Started | Team | 2026-11-08 | 2026-11-12 | 5
2026-07-06 | Integrate emotion predictions, labels and optional icons | Not Started | Team | 2026-11-09 | 2026-11-13 | 5
2026-08-06 | Record attendance and prevent unintended duplicate entries | Not Started | Team | 2026-11-10 | 2026-11-15 | 6
2026-09-06 | Complete first integrated webcam demonstration | Not Started | Team | 2026-11-16 | 2026-11-18 | 3
Task 7 | Task 7 - EVALUATION, INNOVATION & TESTING | Not Started | All Members | 2026-11-04 | 2026-11-24 | 21
2026-01-07 | Create integrated test matrix and nominate testing coordinator | Not Started | Team | 2026-11-04 | 2026-11-07 | 4
2026-02-07 | Agree feasible, attendance-related individual innovative features | Not Started | Team | 2026-11-04 | 2026-11-09 | 6
2026-03-07 | Implement and demonstrate individually assigned innovations | Not Started | Team | 2026-11-09 | 2026-11-17 | 9
2026-04-07 | Compare final model scores and justify selected face verifier | Not Started | Team | 2026-11-06 | 2026-11-11 | 6
2026-05-07 | Test known/unknown people and print, photo and screen spoofs | Not Started | Team | 2026-11-15 | 2026-11-20 | 6
2026-06-07 | Resolve bugs and improve system reliability and response time | Not Started | Team | 2026-11-17 | 2026-11-21 | 5
2026-07-07 | CODE FREEZE: final regression testing only (22–24 November) | Not Started | Team | 2026-11-22 | 2026-11-24 | 3
Task 8 | Task 8 - REPORTS, VIDEO, PEER REVIEW & HAND-IN | Not Started | All Members | 2026-11-12 | 2026-11-25 | 14
2026-01-08 | Draft group report methodology: system architecture, datasets, training and losses | Not Started | Team | 2026-11-12 | 2026-11-17 | 6
2026-02-08 | Draft results/discussion with model performance comparisons | Not Started | Team | 2026-11-17 | 2026-11-20 | 4
2026-03-08 | Write individual contribution, challenges, solutions and innovation reports | Not Started | Team | 2026-11-16 | 2026-11-20 | 5
2026-04-08 | Prepare equal-time continuous demonstration running order | Not Started | Team | 2026-11-17 | 2026-11-19 | 3
2026-05-08 | Rehearse live webcam demonstration and clear presentation blockers | Not Started | Team | 2026-11-19 | 2026-11-20 | 2
2026-06-08 | Finalize group report and individual reports before code freeze | Not Started | Team | 2026-11-20 | 2026-11-21 | 2
2026-07-08 | Record one-take video and publish an accessible link | Not Started | Team | 2026-11-21 | 2026-11-21 | 1
2026-08-08 | Complete self- and peer-evaluation forms | Not Started | Team | 2026-11-20 | 2026-11-21 | 2
2026-09-08 | Submit source code, reports and video link through Canvas | Not Started | Team | 2026-11-25 | 2026-11-25 | 1
2026-10-08 | Prepare for Week 12 technical interviews | Not Started | Team | 2026-11-19 | 2026-11-21 | 3

## Communication Plan
COMMUNICATION PLAN TEMPLATE
STAKEHOLDERS | DELIVERABLE | FREQUENCY | PRIORITY | OWNER | PREFERRED DELIVERY METHOD | COMMENTS
All Team Members | Project updates and task progress | Weekly | High | Project Manager | Messenger/Google Meet | Share progress, completed tasks, and upcoming activities.
All Team Members | Team check-ins and meetings | Weekly | High | Project Manager | Messenger/Google Meet | Hold a 30-minute meeting to discuss progress, challenges, and next steps.
All Team Members | Questions and urgent issues | As needed | High | All Team Members | Messenger/Google Meet | Respond within 4 working hours to urgent messages.
All Team Members | Documents and project deliverables | As needed | High | Assigned Task Owners | Messenger/Google Meet | Store files in shared folders and keep documents updated.
Project Supervisor / Lecturer | Project progress reports | Bi-weekly | High | Project Manager | Messenger/Google Meet | Provide progress summaries, risks, and key milestones.
All Team Members | Meeting minutes and action items | After each meeting | Medium | Meeting Secretary | Messenger/Google Meet | Share meeting notes and assigned tasks within 24 hours.